## 5YR Cap Roll up
TOWN OF HAMILTON CAPITAL IMPROVEMENT PLAN | [11 empty] | 2019-12-10
Potential Year change: Could be pushed out a year.
|  |  |  | Current year | approved
Department | for '21 |  | Item | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total | Comments
Joe D. | Priority | Proj ID#
General |  | G - 1 | Voting machines | Current year FY 19: 0; approved FY '20: 21300 | 21300
|  |  | IT server needs | approved FY '22: 0 | 0 | Shared services? Dec 10th meeting; Schools & Library?
|  | Sub total |  | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 21300
Tim Olson | Priority | Proj ID# | [9 empty] | Joint large equipment purchases with Wenham?
Vehicle |  | V-1 | GMC Dump Truck | approved FY '20: 58000 | 58000 | ordered
| 5 | V-2 | Planer Attachment for John Deere Loader | approved FY '21: 35000 | 35000 | Prep for pavement, should this be outsourced
| 4 | V-3 | Grading Blade for John Deere | approved FY '21: 10000 | 10000 | For gravel roads. Determine use, could it be a shared asset
|  | V-4 | 2013 John Deere Riding mower | approved FY '22: 16129 | 16129
|  | V-5 | 2006 John Deere Backhoe | approved FY'23: 125000 | 125000
|  | V-6 | 2001 John Deere Tractor | approved FY'23: 28375 | 28375
|  | V-7 | 2002 John Deer Tractor | approved FY'24: 28375 | 28375
|  | V-8 | 1998 Flatbed Trailer | approved FY'24: 5500 | 5500
|  | V-9 | (2) 2013 International Sanders | approved FY'23: 150000; approved FY'24: 150000 | 300000
|  | sub total |  | 0 | 58000 | 45000 | 16129 | 303375 | 183875 | 0 | 606379
Tim Olson | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Highways | 2 | H-1 | Road and Sidewalk repairs | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 |  | 540000 | Incremental to chapter 90. Chapter 90 ~$240k annually
| 1 | H-2 | NPDES Phase III-V Complancy | FY 19: 60000; FY '21: 54000; FY '22: 60000; FY'23: 60000 | 234000 | Manadated by EPA
|  | H-3 | Chebacco Road Paving | FY '20: 1000000 | 1000000 | How does this impact yearly budgets when bonded?
|  | sub total |  | 150000 | 1090000 | 144000 | 150000 | 150000 | 90000 | 0 | 1774000
Tim Olson | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Facilities |  | F-1 | COA Partition Wall | FY 19: 5800 | 5800
|  | F-2 | Town Hall Rool Repairs | FY 19: 10000 | 10000
|  | F-3 | Town Hall Renovations | FY 19: 100000; FY '20: 75000 | 175000
|  | F-4 | Install Insulation at Public safety | FY 19: 10000 | 10000
|  | F-5 | Upgrade to ventilation & AC fans ECO | FY 19: 10000 | 10000
|  | F-6 | Town Hall Renovations Borrowed | FY '20: 467767 | 467767
| 3 | F-7 | DPW yard Replacement of Fuel system | FY '21: 250000 | 250000 | Pilot above ground tank at Iron Rail with Wenham
| 3 | F-8 | Town Hall Construction | FY '21: 9700000 | 9700000 | Inflates FY'21 capital, how should this be budgeted?
| 1 | F-9 | PSB HVAC/Boiler Replacement | FY '21: 70000 | 70000 | Should be replaced for FY'21 fiscal year. July AC turn on
|  | F-10 | DPW salt shed replacement | FY '22: 50000 | 50000
|  | F-11 | DPW Garage Roof | FY '22: 50000 | 50000
0
|  | sub total |  | 135800 | 542767 | 10020000 | 100000 | 0 | 0 | 0 | 10798567
Tim Olson | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Water | 3 | W-1 | Meter Replacement | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 |  | 90000 | Based on cost per meter should this be Capitalized?
| 1 | W-2 | Hydrant & Gate Valve Replacement | FY '21: 15000; FY'23: 15000 | 30000 | Public safety, should all be funded.
|  | W-3 | 2013 GMC water Utility Vehicle w/Plow | FY'24: 45000 | 45000
| 1 | W-4 | Water Storage Tank- Eval & Concept design | FY '21: 30000 | 30000 | Shared cost with GCTS
| 3 | W-5 | Phase 5 water Dist upgrades-Pines Nghbrd | FY '20: 1600000; FY '21: 1500000 | 3100000 | Could push out a year.
|  | W-6 | Browns Hill Water Storage tank Design/Const. | FY'23: 3000000 | 3000000 | Should this hit all in one year - debt service?
|  | W-7 | New 2nd Water Tank Alternative site | FY'24: 3000000 | 3000000 | Should this hit all in one year - debt service?
|  | W-8 | Cebacco Road Water main | FY'24: 1500000 | 1500000 | Should this hit all in one year - debt service?
|  | W-9 | Water Treatment Plant | FY '20: 1500000 | 1500000 | Process for organics, satellite well? In design. Approved
|  | sub total |  | 15000 | 3115000 | 1560000 | 15000 | 3030000 | 4560000 | 0 | 12295000
Tim Olson | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Cemetery |  | C-1 | Road Pavement of new section | FY 19: 25000 | 25000
|  | sub total |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Sean Timmons | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Parks & Rec |  | PR-1 | Gym Floor refurbish | FY 19: 12000 | 12000
*Regional |  | PR-2 | Playground equip - rec center | FY'23: 40000 | 40000 | CPC funding?
|  | PR-3 | Patton Park-Concession, bath | FY '20: 50000 | 50000
|  | PR-4 | Donovan Field Re-develop | FY'24: 0 | 0 | $65k removed, FY24, add back if turf field is denied.
|  | PR-5 | Patton Park- Re-develop | FY'24: 0 | 0 | $65k removed, FY24, add back if turf field is denied.
|  | PR-6 | Outdoor BBall Hoops Replace | FY 19: 10000 | 10000 | completed
|  | PR-7 | HWRSD Turf Field | FY '22: 0 | 0 | School budget - reminder $500k in reserve. - Pingree Field?
| 3 | PR-8 | Patton Park Re_dev.& drainage | FY '21: 50000; FY '22: 150000 | 200000 | To cure flooding in park area. CPC funding?
|  | sub total |  | 22000 | 50000 | 50000 | 150000 | 40000 | 0 | 0 | 312000
Kim Driscoll | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Library | 1 | L-1 | Replace roof | FY '21: 75000 | 75000 | Wenham. $7k spent to date, warranty check. Fy'22?
*Regional | 4 | L-2 | Replace server | FY '21: 18000 | 18000 | combine with Town Hall shared server
|  | L-3 | HVAC retrofit | FY '22: 130000 | 130000
|  | L-4 | WiFi access | FY '22: 10000 | 10000 | is this Opex, for capacity.
|  | L-5 | Replace carpet on floors 1 and 2 | FY'23: 85000 | 85000
0
|  | sub total |  | 0 | 0 | 93000 | 140000 | 85000 | 0 | 0 | 318000
Russ Stevens | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Police | 1 | P-1 | Patrol SUV | 38750 | 40000 | 55000 | 56000 | 57000 | 58000 |  | 304750 | Vehicles schedule? Salvage Value ~ 2.9K
|  | P-2 | Camera System | FY 19: 8500 | 8500
|  | P-3 | Magnetic Swipe Card System | FY 19: 25000 | 25000
|  | P-4 | Ballistic Vests | FY '22: 9000 | 9000
|  | P-5 | Fire Arms | FY'23: 8250 | 8250 | Any federal programs or trade in value.
|  | sub total |  | 72250 | 40000 | 55000 | 65000 | 65250 | 58000 | 0 | 355500
Ray Brunet | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Fire Dept |  | F-1 | Pumper-Engine 1 (1996) | FY 19: 550000 | 550000
|  | F-2 | PU Truck- Squad 7 (2008) | FY '20: 48703 | 48703
| 1 | F-3 | Squad truck- Squad 5 (2006) | FY '21: 185000 | 185000
|  | F-4 | Extrication tools- (1996) | FY 19: 30000 | 30000
|  | F-5 | Mobile Cascade Unit | FY'23: 100000 | 100000 | Regionalize with Hamilton Ambulance?
|  | F-6 | Defibs on Fire Apperatus | FY '22: 12135 | 12135 | Federal programs
|  | F-7 | Defibs for Town Buildings | FY'23: 10402 | 10402 | Federal programs
| 1 | F-8 | Ballistic Vests | FY '21: 6000 | 6000
|  | F-9 | Ambulence Service | FY 19: Added by Committee. |  | Shared service with wenham. Could add personnel cost.
|  | sub total |  | 580000 | 48703 | 191000 | 12135 | 110402 | 0 | 0 | 942240
Russ Stevens | Priority | Proj ID# |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
ECO | 1 | E-1 | Upgrade ECO Repeaters |  | 0 | 28000 | 28000 | 28000 | 0 |  | 84000 | Public safety, could all be done in FY'21.
|  | sub total |  | 0 | 0 | 28000 | 28000 | 28000 | 0 | 0 | 84000
Affordable Housing |  |  |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
0
|  | sub total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Open Space |  |  |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
0
|  | sub total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total Town |  |  |  | 1000050 | 4965770 | 12186000 | 676264 | 3812027 | 4891875 | 0 | 27531986
Julie Kukenberger |  |  |  | FY 19 | FY '20 | FY '21 | FY '22 | FY'23 | FY'24 | FY'25 | Total
Schools |  |  | Combined Total |  | 0 | 986500 | 2828500 | 2708500 | 2576000 | 2621182 | 11720682 | Includes Turf. Next meeting Dec 11 to prioritize capital
*Regional
|  | sub total |  | 0 | 0 | 986500 | 2828500 | 2708500 | 2576000 | 2621182 | 11720682
Total Total |  |  |  | 1000050 | 4965770 | 13172500 | 3504764 | 6520527 | 7467875 | 2621182 | 39252668
Regional departments will be split with Wenham
Priorities are set for fiscal year 2021 only.
FY'19 and FY'20 costs are assumed approved. Town finance should determine any project carryover costs needed for FY'21 budget
Project ID's created by Cap Committee, should be replaced by Finance Department if adopted.
Priority Table
| 1 | Eliminates a hazard to public health and safety or required by state or federal laws and regulations.
| 2 | Uses outside financing sources , such as grants
| 3 | Supports adopted plans, goal, objectives and policies, or stabilizes or reduces operating costs, or makes better use of a facility or replaces a clearly obsolete one.
| 4 | Maintains or improves productivity or existing standards of service, or directly benefits the Town's economic base by increasing property values, or provides new programs having social, cultural, historic, environmental, economic or aesthetic value.
| 5 | Increases operational or personnel costs Lacking an ROI
Additional notes
Shared servcies opportunity. Commission Town Fincoms or dept heads to meet and discuss
Affordable housing? Town will likely be asked to contribute, CPC funding?
Patton Homestead? Additional funds will be needed to fulfull future use plans.
No Captial to support future solar projects.
Grant writing, need someone to identify future grants that match our needs and write them. In FY'21 budget?

## Liaison Assignment
Town of Hamilton Capital Committee - Liaison Roles, effective 25 June 2019
The liaison helps the CapCom by communicating information from other boards among its members. The liaison attends relevant meetings to listen, help answer questions and to help prepare for joint meetings with other boards. The liaison role should not be interpreted as the only communication path with the CapCom but it is the primary means to help with interaction amongst the Town's boards & committees.
Board/Committee/Agency | Jack Lawrence | Heather Ford | Dave Thompson | Bill Wilson | Bob Woodbury
Board of Selectmen |  | X
Community Preservation Committee | X
Department of Public Works |  | X | X
Finance and Advisory Committee | X
Finance Director | X
Hamilton Wenham Recreation Board |  |  |  |  | X
Library |  |  |  |  | X
Hamilton Wenham School Committee |  |  |  | X
HWRSD |  |  |  | X
Open Space Committee |  |  |  |  | X
Public Safety |  |  |  | X
Town Manager |  | X
Affordable Housing Trust | X
Town Owned Assets